Annual session 2013

3 to 14 June 2013, New York

Item 7 of the provisional agenda

Evaluation

Management response to the evaluation of the regional programme for the Arab States, 2010-2013

Context, background and findings

1.	The present document constitutes the response of UNDP management to the independent evaluation of the UNDP regional programme for the Arab States, 2010-2013.  The regional programme was approved by the Executive Board in decision 2010/12 at its first regular session 2010. The evaluation was commissioned by the UNDP Evaluation Office to assess the overall programme performance and outcomes of the regional programme. A meta-evaluation of the programme assessed its strategic position, achievement of intended goals and results, performance of policy advice, knowledge management and capacity development activities, synergies and partnerships.

2.	The evaluation, conducted in 2012, is intended to feed directly into the development of the fifth regional programme document for the Arab States, 2014-2017. The aim of the evaluation is to provide accountability for the achievement of results and resources used, identify successful approaches and challenges, and learn lessons from implementation in a regional setting. The evaluation was structured around the customary international evaluation criteria of relevance, effectiveness, efficiency and sustainability. It presents findings, conclusions and recommendations resulting from the assessment of UNDP performance and its strategic positioning in the region.

3.	The evaluation concluded that the regional programme for the Arab States, 2010-2013, has been implemented at a challenging time in the region’s history. It was designed and launched before the Arab uprisings of 2011 and, at the time, UNDP was among the very few aid organizations trying to promote good governance in the region. It will now need to adapt and take into account the changes transforming the region.

4.	Management notes that the evaluation focused largely on implementation and structural aspects of the regional programme’s management, and less on the substantive focus that the Regional Bureau for Arab Sates (RBAS) considers key. In the annex to the present document, following the standard template, UNDP management presents detailed responses to each of the recommendations and some key issues, and proposes follow-up action with timeframe specified.

Annex. Key recommendations and management response

| Evaluation recommendation 1 In order to enhance its visibility in the region and increase its chances of success and sustainability, the regional programme for the Arab States should be more firmly anchored in, and managed from, the Arab region, and should strengthen its partnerships with regional organizations. |
| --- |
| Management response Noted and partially initiated. While the regional programme is firmly anchored in the region, with all regional projects based in and managed from the region, it is agreed that additional efforts need to be made to further engage with regional organizations. RBAS signed a memorandum of understanding with the League of Arab States in September 2012. Since 2011, the League of Arab States has been involved in regional projects development. The Economic and Social Commission for Western Asia was involved in the development of the Arab Climate Resilience Initiative. The League of Arab States is also a partner in the new regional project on trade entitled Aid for Trade in Arab States – implementation starting in 2013. |
| Key actions | Timeframe | Responsible unit(s) |
| Pursue ongoing consultations with the League of Arab States to better identify possible opportunities for cooperation and provision of support. | 2013 | RBAS |
| Ensure greater involvement and coordination with regional organizations in the development and implementation of regional projects, particularly through the regional United Nations Development Group mechanism. | 2014-2017 | RBAS |
| Evaluation recommendation 2 Project managers located in the region should be: empowered to manage their project’s personnel and financial resources; encouraged to cultivate a rapport with donors and to participate in resource mobilization efforts; and allowed to strengthen links with other UNDP units and external partners. |
| Management response Partially relevant. Project managers contribute to resource mobilization efforts. However, they cannot be in charge of resource mobilization on their own, as there would be an issue of segregation of duties. Furthermore, it is a corporate agreement that for regional projects, regional bureaux, in cooperation with the Bureau of External Relations and Advocacy, Bureau for Development Policy and Bureau for Crisis Prevention and Recovery, should take the lead in resource mobilization efforts in order to ensure better coherence and avoid duplication and donor fatigue. As per the UNDP Internal Control Framework, “The broad responsibilities of project managers include: - Preparing annual budgets and workplans for approval by office management; - Achieving the outputs described in the workplan; - Reviewing budgets and workplans on a monthly basis and bringing to the attention of senior management any proposed changes; - Prepare procurement and recruitment plans for the project, and monitor activities based on the plans developed.” Project managers manage human and financial resources within this framework, while the ultimate accountability for the use of regional funds rests with the Regional Director. Partners and other UNDP units are always invited to participate and contribute to regional projects organized events. |
| Ensure project managers continue to reach out and involve other UNDP units and external partners in project activities, subject to availability of funds. | 2013-2017 | RBAS |
| Evaluation recommendation 3 The regional programme should be better connected to the UNDP knowledge architecture. The most effective way to achieve this would be to place regional projects and project managers under the responsibility of the Regional Centre in Cairo, as is standard practice in other regions, with RBAS at headquarters retaining only an oversight role. |

| Management response Noted. The Regional Bureau for Arab States is currently undergoing a change management exercise, looking at reviewing the bureau’s structure in order to optimize efficiency. Currently, projects are all based in and managed from the region, with headquarters only having an oversight role. |
| --- |
| Upon completion of the work of the UNDP Management Consulting Team (MCT), revise the current bureau architecture and implement changes as appropriate. | 2013-2014 | RBAS |
| Evaluation recommendation 4 The regional programme should strengthen its internal coherence; connect more systematically project outputs and activities with expected outcomes in the regional programme document; strengthen collaboration between regional programme components; and document and communicate regularly about the funding, activities and results of the regional programme as a whole. |
| Management response It is agreed that the regional programme should strengthen its internal coherence and enhance its documentation and communication of the programme’s achievements. |
| Align the new regional programme with the UNDP strategic plan, 2014-2017, and emphasize resilience as the cross-cutting theme to strengthen connections and linkages across different areas of focus on poverty reduction, governance, and energy and environment for improved internal coherence. Further underline the importance of inclusion, especially targeting youth and gender, in all focus areas, and reflect them in relevant knowledge products and communication materials. | 2014-2017 | RBAS |
| Organize annual knowledge cross-sharing meetings in order to provide a platform of exchange between regional projects, and to use as a basis for consolidation of project outputs at the outcome level. | 2014-2017 | RBAS |
| Develop a quarterly newsletter that includes main achievements of the regional programme. | 2014-2017 | RBAS |
| Evaluation recommendation 5 The regional programme should build upon the current positioning as a source of carefully contextualized regional knowledge and expertise in Arabic, English and French, and build on the comparative advantages of regional projects and programmes in advocacy on sensitive issues, socio-economic and political context analysis, knowledge sharing, regional debates and dialogue and use of South-South cooperation. |
| Management response Partially agreed and initiated. The regional programme recognizes the importance of making knowledge products accessible to most, and for this reason has been developing knowledge and making it available in mainly Arabic and English for the past few years. Whenever possible, and subject to availability of funds, French versions of publications have also been produced. The regional programme will also continue building upon its current positioning to provide a platform for debate and knowledge production in the region. The ongoing change management exercise is looking at various implementation options for regional projects. Country-level activities are always planned, coordinated and implemented in full cooperation with country offices. |
| Review implementation arrangements of regional projects based on MCT recommendations. | 2013-2014 | RBAS |
| Continue producing knowledge and making it available in Arabic, English, and where possible, in French, and maintain its role in addressing issues that may be sensitive when tackled at the national level. | 2013-2017 | RBAS |
| Evaluation recommendation 6 The regional programme should take into account the changes transforming the region, articulate more explicit support to regional efforts to protect human rights, and attempt to translate information and knowledge into action, so as to contribute to concrete outcomes that can improve people’s lives. |
| Management response Agreed. The new regional programme, 2014-2017, will consider the various development issues, including gender, affecting the region following the changes transforming it, and prioritize interventions subject to availability of funding. In doing so, RBAS will be guided as well by the outcomes of national and regional consultations on MDG post-2015 development priorities. |
| Ensure the new regional programme, 2014-2017, focuses on development issues affecting the region, taking into account the changes transforming it, and within the framework of the Executive Board approved UNDP strategic plan, 2014-2017. | 2014-2017 | RBAS |
| Evaluation recommendation 7 UNDP in the Arab States should expand its partnerships with civil society and engage with community organizations, religious leaders, the media and academia in debates, awareness raising activities, and assessment of public policy. |
| Management response Noted and applied in several regional projects (for example, HIV/AIDS Regional Programme for the Arab States, Anti-Corruption and Integrity in the Arab Countries). The regional programme has been successful in building networks, bringing together governmental and non-governmental actors and stakeholders, particularly in the area of anti-corruption, through the Arab Anti-Corruption and Integrity Network. The regional programme has also adopted this participatory approach in regional project development, and will continue doing so during the next programming cycle, 2014-2017. |
| Ensure the new regional programme, 2014-2017, continues to foster participation of all stakeholders, and clearly mention this approach in the regional programme document, 2014-2017. | 2014-2017 | RBAS |
| Evaluation recommendation 8 RBAS should commission more frequent outcome evaluations and audits of its regional programme. |
| Management response It is agreed that RBAS should commission more regular outcome evaluations. |
| Commission at least two outcome evaluations during the programming cycle, 2014-2017 | 2014-2017 | RBAS |