Annex 1

# UNCDF Integrated Results and Resources Matrix 2014-2017 (Results as of 2015)

April 2016

# Part A - Development Effectiveness

| Outcome 1: Financing increased for basic services and inclusive growth/local economic development Resources: At the mid-point, UNCDF achieved a resource target of US$49million (against the 2014-2017 target of US$ 117million) for outcome 1. The shortfall in core (regular) resources was counter-balanced by multi-year non-core resources that hit a peak in 2014. |
| --- |
| Outcome Indicators: (assess progress against specified outcomes; they help verify that the intended positive change in the development situation has actually taken place) | Baseline (2013, unless noted) | Year Baseline | Actual 2014 | Actual 2015 | Cumulative targets | Implementation rate at mid- point of strategic framework | Implementation rate against cumulative target |
| Inclusive Finance |
| 1.a Net change of domestic savings mobilized by UNCDF supported Financial Service Providers (FSPs) leveraged by UNCDF contribution | 10 to 1 | 2013 | 36 to 1 | 159.7 to 1 | 10 to 1 | 1597% | 1597% |
| Local Development Finance |
| 1.b Net increase in local fiscal space available for local development in sub-national territorial jurisdictions supported by UNCDF | - | 2013 | Not available (NA) | 425% | 100% | 850% | 425% |
| 1.c Gross increase in fixed capital formation comprised of individual projects/investments under $20m located within sub-national territorial jurisdiction supported by UNCDF | - | 2013 | NA | NA | NA | NA | NA |
| Outputs(UNCDF provides specific support for the following results) | Output Indicators (output indicators measure only those results from schemes, services, plans, actions, etc., which are specifically supported by UNCDF.) | Baseline (2013, unless noted) | Year Baseline | Actual 2014 | Actual 2015 | Cumulative targets | Implementation rate at mid- point of strategic framework | Implementation rate against cumulative target |
| Inclusive Finance |
| Output 1.1 Improved performance of sustainable, healthy, responsible FSPs leveraging UNCDF funds (to be measured in terms of sustainability, portfolio quality, outreach, responsible provision of financial services) | Financing for development: effect of UNCDF core funding on resources for inclusive finance |
|  | 1.1.1 Change from baseline in value of loan portfolio of FSPs leveraged by UNCDF core contribution (denominator) | 10 to 1 | 2013 | 56 to 1 | 46 to 1 | 10 to 1 | 460% | 460% |
|  | 1.1.2 Change from baseline in value of savings portfolio of FSPs leveraged by total UNCDF core contribution (denominator) | 10 to 1 | 2013 | 36 to 1 | 160 to 1 | 10 to 1 | 1597% | 1597% |
|  | Sustainability: Improvements in FSP profitability/sustainability. Improvements in portfolio quality |
|  | 1.1.3 Percentage of FSPs that have audited financial statements | 81% | 2013 | 90% | 99% | 90% | 110% | 110% |
|  | 1.1.4 Percentage of FSPs making progress toward profitability targets (return on assets) | 73% | 2013 | 75% | 76% | 80% | 95% | 95% |
|  | 1.1.5 Percentage of FSPs meeting portfolio quality targets (PAR 30 days) | 55% | 2013 | 59% | 62% | 80% | 78% | 78% |
|  | Responsibly-provided services |
|  | 1.1.6 Percentage of FSPs that endorse SMART Campaign Client Protection Principles (CPPs) or equivalent | 82% | 2013 | 74% | 95% | 89% | 106% | 107% |
| Local Development Finance |
| Output 1.2 Improved performance of sustainable, accountable local governments and improved performance of revenue-generating projects. Measured in terms of how UNCDF supports capacity to mobilize, allocate, invest and make accountable resources for effective local development. | Improved performance of sustainable, accountable local governments, and improved performance of revenue generating projects. Measured in terms of how UNCDF supports capacity to mobilize resources for effective local development. |
|  | 1.2.1-a Change from baseline in value of total national budget allocated to local governments leveraged by UNCDF contribution | 5% | 2013 | 12% | 47% | 50% | 188% | 94% |
|  | 1.2.1-b Change from baseline in own revenue mobilized by local governments leveraged by UNCDF contribution | 5% | 2013 | 0.7% | NA | NA | NA | NA |
|  | 1.2.2 Change from baseline in value of domestic capital mobilized to the local level leveraged by UNCDF contribution | 10% | 2013 | 8.50% | 3730% | 25% | 29840% | 14920% |
|  | 1.2.3 Change from baseline in value of government to person (G2P) systems leveraged by UNCDF contribution | 0% | 2013 | NA | NA | NA | NA | NA |
|  | Improved performance of sustainable, accountable local governments, and improved performance of revenue generating projects. Measured in terms of how UNCDF supports capacity to allocate resources for effective local development. |
|  | 1.2.4 Number of Local Institutions that improve performance against selected Public Expenditure and Financial Accountability (PEFA) indicators | 111 | 2013 | 79 | 17 | 80 | 240% | 120% |
|  | PEFA performance indicator (PI)-8: Transparency of inter-governmental fiscal relations at the sub-national level | 57 | 2013 | 57 | 6 | NA | NA | NA |
|  | PEFA PI-12: Multi-year perspective in fiscal planning, expenditure policy and budgeting | 31 | 2013 | 12 | 11 | NA | NA | NA |
|  | PEFA PI-19: Competition, value for money and controls in public procurement | 23 | 2013 | 10 | 0 | NA | NA | NA |
|  | 1.2.5 Number of investment projects reaching financial closure following effective investment appraisal (Local Finance Initiative: LFI) | - | 2013 | 1 | 15 | NA | 107% | NA |
|  | 1.2.6 Number of G2P mechanisms at local level that incorporate and adopt UNCDF design features involving local-level institutions in planning, targeting, monitoring, and redress | - | 2013 | - | NA | NA | NA | NA |
|  | Improved performance of sustainable, accountable local governments, and improved performance of revenue generating projects. Measured in terms of how UNCDF supports capacity to invest resources for effective local development. |
|  | 1.2.7 Number and type of local investments in infrastructures and services completed | 1,500 | 2013 | 1,880 | 1,549 [+ data reconciliation for 2014 = -133] | 6,350 | 104% | 52% |
|  | 1.2.8 Number of UNCDF-supported local institutions that improve performance against investment-related PEFA indicators | NA | 2013 | NA | NA | NA | NA | NA |
|  | 1.2.9 Number of local investments in UNCDF-supported revenue-generating private and public/private infrastructure and services complying with financial projections | 7 | 2013 | 3 | 6 | 15 | 120% | 60% |
|  | Improved performance of sustainable, accountable local governments, and improved performance of revenue generating projects. Measured in terms of how UNCDF supports capacity to make accountable the resources that are invested in local development. |
|  | 1.2.10 Number of local institutions that improve performance against accountability related PEFA indicators | 156 | 2013 | 43 | 15 | 80 | 145% | 73% |
|  | PEFA PI-10: Access to key fiscal information at the sub national level - refers to access of the general public at the location (‘local’ public access) or at least the relevant interest group | 30 | 2013 | 30 | - | NA | NA | NA |
|  | PEFA PI-11: Orderliness and participation in the annual budget process | 126 | 2013 | 13 | 15 | NA | NA | NA |
|  | 1.2.11 Number of G2P mechanisms at the local level that include locally-accessible redress systems | - | 2013 | NA | NA | NA | NA | NA |
|  | 1.2.12 Number of revenue-generating projects with multi-stakeholder boards | 7 | 2013 | 7 | 9 | 15 | 213% | 107% |
| Outcome 2: Effective financing mechanisms established to increase resilience to economic and environmental shocks Resources: At the mid-point, UNCDF achieved a resource target of US$49million (against the 2014-2017 target of US$ 117million) for outcome 2. The shortfall in core (regular) resources was counter-balanced by multi-year non-core resources that hit a peak in 2014. |
| Outcome Indicators | Baseline (2013, unless noted) | Year Baseline | Actual 2014 | Actual 2015 | Cumulative targets | Implementation rate at mid- point of strategic framework | Implementation rate against cumulative target |
| Inclusive Finance |
| 2.a Number of new products to improve client security, resilience against shocks and extend the frontiers of inclusive finance | 45 | 2013 | 48 | 28 [+ data reconciliation for 2014 = -20] | 155 | 75% | 36% |
| 2.b Number of clients served by these new products | - | 2013 | 1,031,167 | 1,164,259 | 6,400,000 | 36% | 34% |
| Local Development Finance |
| 2.c Number of public and private financing systems (designed and piloted) for local infrastructure and services that improves resilience of local governments and their populations to shocks (increasing resilience of populations, environment, built environment, productive systems) | - | 2014 | 3 | 5 [+ data reconciliation for 2014 = +11 | 25 | 152% | 76% |
| 2.d Number of local government jurisdictions served by these new systems as they are upscaled | - | 2013 | - | 26 | NA | NA | NA |
| Outputs(UNCDF provides specific support for the following results) | Output Indicators (output indicators measure only those results from schemes, services, plans, actions, etc., which are specifically supported by UNCDF.) | Baseline (2013, unless noted) | Year Baseline | Actual 2014 | Actual 2015 | Cumulative targets | Implementation rate at mid- point of strategic framework | Implementation rate against cumulative target |
| Inclusive Finance |
| Output 2.1 Improved access to and usage of basic financial services as an effective way to reduce vulnerability and shocks | 2.1.1 Total number of clients served via products that strengthen client resilience to shocks (MM4P, BTCA, Clean Energy, Micro Insurance) | - | 2013 | 4,982,232 | 6,498,526 | 6,400,000 | 203% | 179% |
|  | 2.1.2 Number of product innovations in areas such as youth finance, agricultural/rural finance, mobile money or cash to electronic transitions | - | 2013 | 48 | 28 | 155 | 101% | 49% |
| Local Development Finance |
| Output 2.2 Improved access to and usage of public and private local investments as an effective way to reduce vulnerability and shocks | 2.2.1 Number of new systems targeting vulnerability and shocks in place | - | 2013 | 14 | 5 | 25 | 152% | 76% |
|  | 2.2.2 Volume and quality of G2P transfers targeting vulnerability and shocks in place | - | 2013 | 1,200,619 | NA | NA | NA | NA |
|  | 2.2.3 Number of innovations in relevant local development finance systems introduced by UNCDF | - | 2013 | NA | NA | NA | NA | NA |
| Outcome 3: Policy environments fostered that enable sustainable financing for development Resources: At the mid-point, UNCDF achieved a resource target of US$24 million (against the 2014-2017 target of US$ 58 million) for outcome 3. The shortfall in core (regular) resources was counter-balanced by multi-year non-core resources that hit a peak in 2014. |
| Outcome Indicators | Baseline (2013, unless noted) | Year Baseline | Actual 2014 | Actual 2015 | Cumulative targets | Implementation rate at mid- point of strategic framework | Implementation rate against cumulative target |
| Inclusive Finance |
| 3.a Number of improvements to the policy environment and enabling ecosystem, including client protection, resulting from UNCDF advocacy and support. | 11 | 2013 | 15 | 9 | 85 | 126% | 28% |
| Local Development Finance |
| 3.b Policy environments fostered that enable increased financing for local development (public and private) | - | 2013 | 4 | NA | NA | NA | NA |
| Outputs(UNCDF provides specific support for the following results) | Output Indicators (output indicators measure only those results from schemes, services, plans, actions, etc., which are specifically supported by UNCDF.) | Baseline (2013, unless noted) | Year Baseline | Actual 2014 | Actual 2015 | Cumulative targets | Implementation rate at mid- point of strategic framework | Implementation rate against cumulative target |
| Inclusive Finance |
| Output 3.1 UNCDF- funded diagnostic tools/advocacy initatitives provide a key contribution to shaping national governments’ agendas on financial inclusion | 3.1.1 Number of diagnostics on financial inclusion completed (public goods) | 22 | 2013 | 19 | 23 | 53 | 124% | 79% |
|  | 3.1.2 Number of inclusive finance road maps, action plans or national strategies adopted | 6 | 2013 | 8 | 10 | 35 | 86% | 51% |
|  | 3.1.3 Number of commitments to Better than Cash Alliance (BTCA) to transition cash to electronic payments | 4 | 2013 | 35 | 42 | 35 | 280% | 120% |
|  | 3.1.4 Number of capacity building activities completed to strengthen the capacity of regulators/supervisors, especially to safeguard poor people’s savings. | 15 | 2013 | 52 | 46 | 118 | 392% | 83% |
|  | 3.1.5 Number and quality of approved UNCDF publications (inclusive finance) | 19 | 2013 | 62 | 62 | 130 | 210% | 95% |
| Local Development Finance |
| Output 3.2 UNCDF-funded diagnostic tools/advocacy initiative provide a key contribution to shaping national governments’ agendas in local development finance | 3.2.1 Number of local development diagnostics completed | 2 | 2013 | 80 | 31 [+ data reconciliation for 2014 = -17] | 150 | 125% | 63% |
|  | 3.2.2 Number of national strategies or action plans for local development finance adopted | 2 | 2013 | 36 | 34 [+ data reconciliation for 2014 = -9] | 120 | 102% | 51% |
|  | 3.2.3 Number of policy or regulatory changes on local development finance as a result of UNCDF advocacy on Local Development Finance | - | 2013 | 5 | 7 | NA | NA | NA |
|  | 3.2.4 Number of initiatives to strengthen capacities of national and local actors (training, advocacy, peer to peer learning) | - | 2013 | 25 | 247 [+ data reconciliation for 2014 = +32] | 750 | 81% | 41% |
|  | 3.2.5 Number of approved UNCDF publications (local development) | - | 2013 | 0 | 60 [+ data reconciliation for 2014 = +32] | 180 | 102% | 51% |

# Part B - Institutional Effectiveness

| Institutional Effectiveness: UNCDF is a more effective and efficient organization, with improved systems and business practices and processes, well-managed resources and engaged personnel Resources: At the mid-point, UNCDF has shown reduced management costs against the target of $22 million (2014-2017 target of US$ 52 million) for institutional effectiveness. This is reflected in the improved management efficiency ratio under institutional effectiveness indicator 1.2.6 below. |
| --- |
| Result Statements | Indicators | Baseline (2013, unless noted) | Year Baseline | Actual 2014 | Actual 2015 | Cumulative targets | Implementation rate at mid- point of strategic framework | Implementation rate against cumulative target |
| Output 1.1 Improved quality of programming and accountability for results | Quality of Programming |
|  | 1.1.1 Percentage of programme outcomes that are reported as on-track or achieved | NA | 2013 | 70% | 75% | 90% | 83% | 83% |
|  | Evaluation and Accountability |
|  | 1.1.2 Annual number of results-based evaluations (project, programme and thematic) | 3 | 2013 | 4 | 2 | 14 | 86% | 43% |
|  | 1.1.3 Implementation rate of agreed actions in evaluation management responses | 70% | 2013 | 85.40% | 79% | 80% | 103% | 103% |
|  | Audits |
|  | 1.1.4 Percentage of UNCDF’s programme covered by Office and Audit Investigation (OAI)’s audit annually | 40% | 2013 | 42% | 25% | 40% | 84% | 63% |
|  | 1.1.5 Percentage of audits that are unqualified | 100% | 2013 | 100% | 100% | 100% | 100% | 100% |
|  | 1.1.6 Implementation rate of agreed-upon audit recommendations | 85% | 2013 | 56% | 56% | 100% | 86% | 56% |
|  | Gender Mainstreaming |
|  | 1.1.7 Percentage compliance by UNCDF in at least ‘meeting’ UN System-Wide Action Plan gender reporting requirements across the 15 performance categories | 46% | 2013 | 40% | 53% | 87% | 88% | 61% |
| Output 1.2 Structure of financial resources maximized | Total Resources Mobilized |
|  | 1.2.1 Levels of core+ | 16,000,000 | 2013 | 14,925,892 | 12,456,687 | 86,000,000 | 76% | 32% |
|  | 1.2.2 Levels of non-core (from development partners) | 35,000,000 | 2013 | 53,000,000 | 36,614,415 | 280,000,000 | 60% | 32% |
|  | 1.2.3 Levels of non-core (from private and non-governmental sources) | 13,000,000 | 2013 | 20,000,000 | 9,972,404 | 20,000,000 | 300% | 150% |
|  | 1.2.4 Percentage of delivery against approved budget | 85% | 2013 | 76% | 75% | 90% | 84% | 84% |
|  | 1.2.5 Optimal mobilisation ratio of non-core resources by core funds for programmes/projects | 3:1 | 2013 | 5:1 | 4:1 | 4:1 | 113% | 113% |
|  | Optimised Cost Structure |
|  | 1.2.6 Percentage of total UNCDF expenditure related to management activities (management- efficiency ratio) | 15% | 2013 | 14% | 10.85% | 15% | 83% | 83% |
|  | 1.2.7 Percentage of total UNCDF expenditure on management activities spent on travel costs | 10% | 2013 | 2% | 6% | 10% | 53% | 53% |
|  | 1.2.8 Percentage of total resources going to capital grants (Core) | 30% | 2013 | 17% | 27% | 40% | 55% | 55% |
|  | 1.2.9 Percentage of total resources going to capital grants (Non-core) | 44% | 2013 | 51% | 46% | 50% | 97% | 97% |
| Output 1.3 Strengthened human resource management to attract, develop and retain a diversified and productive workforce | 1.3.1 Percentage of staff who are female at all levels | 27% | 2013 | 45% | 49% | 50% | 94% | 94% |
|  | 1.3.2 Percentage of staff who are female at P5 and above | 28% | 2013 | 30% | 36% | 50% | 66% | 66% |
| Output 1.4 Improved perception of staff working in UNCDF | 1.4.1 Percentage of staff surveyed who expressed confidence in leadership and direction | 70% | 2013 | 64% | NA | 75% | 85% | 85% |
|  | 1.4.2 Percentage of staff surveyed who rate UNCDF favorably on empowerment | 66% | 2013 | 67% | NA | 75% | 89% | 89% |
|  | 1.4.3 Percentage of staff surveyed who rate UNCDF favorably on engagement | 67% | 2013 | 67% | NA | 75% | 89% | 89% |
| Output 1.5 Stronger corporate positioning based on robust internal policies, rigorous analytical work, active engagement in multi-lateral processes (including post-2015) and effective corporate knowledge management | 1.5.1 Number of multi-partner initiatives in which UNCDF is involved globally or regionally where the organisation can influence debate and policy on the basis of its investment mandate | 7 | 2013 | 14 | 24 | 60 | 127% | 63% |
| Output 1.6 UNCDF’s mandate in the LDCs better understand and more widely- communicated to target audiences based on implementation of its communications plans | 1.6.1 a Number of monthly unique visitors to public external website (cumulative) | 6000 | 2013 | 73,979 | 99,278 | 174,000 | 110% | 57% |
|  | 1.6.1 b Number of monthly unique visitors to public external website (per month average) | 6000 | 2013 | 8,392 | 8,273 | 14,500 | 110% | 57% |
|  | 1.6.2 Number of followers on Twitter corporate account | 200 | 2013 | 1,430 | 3,100 | 6,000 | 103% | 52% |
|  | 1.6.3 Number of followers on Facebook corporate account | 500 | 2013 | 94,569 | 122,060 | 180,000 | 111% | 68% |
| Output 1.7 Partnerships strategy implemented with a view to extending the scale and scope of UNCDF’s work | 1.7.1 Number of strategic partnerships effectively managed – and new ones developed leading to contributions to UNCDF core resources | 12 | 2013 | 15 | 13 | 17 | 93% | 42% |
|  | 1.7.2 Number of strategic partnerships effectively managed – and new ones developed – leading to contributions to UNCDF non-core resources | 25 | 2013 | 31 | 32 | 33 | 102% | 48% |
|  | 1.7.3 Number of UNCDF Stakeholder Consultations (informal Executive Board sessions) arranged per year | 2 | 2013 | 1 | 2 | 8 | 75% | 38% |

# Footnotes

The cumulative targets for some indicators have been modified to reflect changes in programme activities during the strategic framework period.

The performance in leverage far exceeded the target of 1:10 (core resources to net change in savings mobilized).  One part of this is due to the shrinking percentage of UNCDF’s programming funded by core resources (denominator).  The indicator has been modified in the proposed revised IRRM to take account of this effect.

As the indicator is measuring a change, the baseline is zero. The average local fiscal space of 87 local governments sampled from Local Development Finance portfolio was US$977,698 in 2013 and this was used as the baseline to calculate a percentage increase each year. Variations within and between countries are large ranging from maximum 4,965 % to minimum -816%.  Data from five countries are not reflected due to delays in collecting the information.

Due to difficulty in collecting the necessary data to calculate the gross progress, this indicator shows as data 'not available'. The indicator has been modified in the revised IRRM to ensure measurement of progress based on available information to be collected at the end of strategic framework period (2014- 2017).

The performance in leverage far exceeded the target of 1:10 (core resources to net change in savings mobilized) due primarily to the shrinking percentage of UNCDF’s programming funded by core resources (denominator).

Ibid.

Due to difficulty in collecting the necessary data, the indicators for 2015 shows as data 'not available'. The indicator has been removed in the revised IRRM. Please refer to Annex 2 for more details on the modified indicators.

The very high increase in domestic capital mobilised in 2015 stems from the difference between what was mobilised by Local Finance Initiative (LFI) in 2014 (1,143,079 USD) and what has been mobilised in 2015 (43,780,000 USD).

Due to no major programme activities related to government to person (G2P) payments, this indicator shows as data 'not available'.  The indicator has been removed in the revised IRRM. Please refer to Annex 2 for more details.

Assessments of UNCDF supported local authorities against PEFA indicators were conducted based on selected samples. Hence the number reported does not represent the totality of the UNCDF support to local authorities. The PEFA indicators have been modified in the revised IRRM to reflect the sample based reporting.

Due to no major programme activities related to G2P payments, this indicator shows as data 'not available'.  The indicator has been removed in the revised IRRM. Please refer to Annex 2 for more details.

The reported figures include an adjustment for the previous year based on a thorough data reconciliation/methodological review process conducted in the context of mid-term review.

Due to difficulty in collecting the necessary data, the indicators for 2015 shows as data 'not available'. The indicator has been removed in the revised IRRM. Please refer to Annex 2 for more details.

Assessments of UNCDF supported local authorities against PEFA indicators were conducted based on selected samples. Hence the number reported does not represent the totality of the UNCDF support to local authorities. The PEFA indicators have been modified in the revised IRRM to reflect the sample based reporting.

Due to no major programme activities related to G2P payments, this indicator shows as data 'not available'.  The indicator has been removed in the revised IRRM. Please refer to Annex 2 for more details.

The reported figures for 2015 include an adjustment for the previous year based on a thorough data reconciliation/methodological review process conducted in the context of mid-term review.

Ibid.

Due to no major programme activities related to G2P payments, this indicator shows as data 'not available'.  The indicator has been removed in the revised IRRM. Please refer to Annex 2 for more details.

Due to difficulty in collecting the necessary data, the indicators for 2015 shows as data 'not available'. The indicator has been removed in the revised IRRM. Please refer to Annex 2 for more details on the modified indicators.

Due to difficulty in collecting the necessary data, the indicators for 2015 shows as data 'not available'. The indicator has been modified in the revised IRRM. Please refer to Annex 2 for more details.

The reported figures for 2015 include an adjustment for the previous year based on a thorough data reconciliation/methodological review process conducted in the context of mid-term review.

Ibid.

Ibid.

Ibid.

As the UNCDF staff survey was not conducted in 2015, the indicator shows as data 'not available' for 2015.

Ibid.

Ibid.