**FULLY-COSTED EVALUATION PLAN (2019-2023)**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **UNDAF/CPD outcome** | **UNDP Strategic Plan Outcome** | **Evaluation title** | **Partners (joint evaluation)** | **Evaluation commissioned by (if other than UNDP)** | **Type of evaluation** | **Planned evaluation completion Date** | **Estimated cost** | **Provisional source of funding**  |
| **All** | **SP Outcome 1 and 2** | Final UNDAF Evaluation  | Government of Benin | UN Coordination Office | UNDAF  | 12/2022  | USD 25,000 | TRAC (UNDP Contribution) |
| **All** | **SP Outcome 1 and 2** | Mid Term CPD Evaluation | Government of Benin  | N/A | CPD  | 09/2021 | USD 70,000 | TRAC (UNDP)  |
| **UNDAF OUTCOME 3** By 2023, Benin population, especially the most vulnerable, are more resilient and have a better quality of life through access to decent employment, food and nutrition security, clean energy, and through the sustainable management of the natural resources, the adverse effects of change climate change, crises and disasters | **Outcome 2:** ACCELERATE STRUCTURAL TRANSFORMATIONS FOR SUSTAINABLE DEVELOPMENT | Project Final Evaluation: PAMCoPRC-CPADD | Government of Benin,Government of Japan  | N/A | Project | 10/2019 | USD 30,000 | Project Budget (Japan) |
| **UNDAF OUTCOME 1** By 2023, Benin population have equal and inclusive access to effective, transparent and accountable institutions and to modern public administrations, at all level, in a climate of peace and security, particularly related to access to justice respectful of human rights. | **Outcome 1:** ADVANCE POVERTY ERADICATION IN ALL ITS FORMS AND DIMENSIONS | Project Mid Term Evaluation: Strengthening the resilience of the Energy sector to climate risks and variability in Benin | Government of Benin, GEF | N/A | Project | 11/2019 | USD 60,000 | Project Budget (GEF)  |
| **UNDAF OUTCOME 1**  | **Outcome 1:** ADVANCE POVERTY ERADICATION IN ALL ITS FORMS AND DIMENSIONS | Project Mid Term Evaluation: Biomass Electricity  | Government of Benin, GEF | N/A | Project | 11/2019 | USD 50,000 | Project Budget (GEF) |
| **UNDAF OUTCOME 1** | **Outcome 1:** ADVANCE POVERTY ERADICATION IN ALL ITS FORMS AND DIMENSIONS | Project Mid Term Evaluation: “Strengthening the resilience of rural livelihoods and sub-national government system to climate risks and variability in Benin” | Government of Benin, GEF | N/A | Project | 11/2020 | USD 50,000 | Project Budget (GEF) |
| **UNDAF OUTCOME 1** | **Outcome 1:** ADVANCE POVERTY ERADICATION IN ALL ITS FORMS AND DIMENSIONS | Project Final Evaluation: Strengthening the resilience of the Energy sector to climate risks and variability in Benin | Government of Benin, GEF | N/A | Project | 09/2021 | USD 60,000  | Project Budget (GEF) |
| **UNDAF OUTCOME 1**  | **Outcome 1:** ADVANCE POVERTY ERADICATION IN ALL ITS FORMS AND DIMENSIONS | Project Final Evaluation: Biomass Electricity  | Government of Benin, GEF | N/A | Project | 09/2021 | USD 50,000 | Project Budget (GEF)  |
| **UNDAF OUTCOME 1**  | **Outcome 1:** ADVANCE POVERTY ERADICATION IN ALL ITS FORMS AND DIMENSIONS | Project Final Evaluation: “Strengthening the resilience of rural livelihoods and sub-national government system to climate risks and variability in Benin” | Government of Benin, GEF | N/A | Project | 11/2022 | USD 50,000 | Project Budget (GEF) |