**ANNEX**. **FULLY-COSTED EVALUATION PLAN**

**Programming Cycle: 2020-2022**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **UNDAF (or equivalent)****Outcome**  | **UNDP Strategic Plan Outcome** | **Evaluation Title** | **Partners (joint evaluation)** | **Evaluation commissioned by (if not UNDP)** | **Type of evaluation** | **Planned Evaluation Completion Date** | **Estimated Cost** | **Provisional Source of Funding** |
| ***Outcome 2*** *By 2022, the vulnerable population is resilient to climate change and disaster risk with sustainable and inclusive production; planning and management of the territory, cities, natural resources and the environment.* | SP Outcome 3 - Build resilience to shocks and crises | Mid-term review of the GEF Address Urgent Coastal Adaption Needs & Capacity Gaps Angola Project | UNDP, MINAMB, UNEP | UNDP/GEF | Project  | March 2020 | $30,000 | GEF project funds |
| ***Outcome 1****: By 2022, the Angolan population, particularly the most vulnerable (children, adolescents, youth, women, people with disabilities), have greater access to quality, integrated, social services as well as to a diversified, job and income creating economy, thereby realizing their rights in accordance with the SDGs* | SP Outcome 1- Advance poverty eradication in all its forms and dimensions. | Midterm Outcome evaluation of the: Inclusive growth and social basic services  | Government of Angola, United Nations agencies, CSO, academia, NGOs, |  | Outcome  | September 2020 | $40,000 | TRAC funds |
| ***Outcome 2:*** *By 2022, the vulnerable population is resilient to climate change and disaster risk with sustainable and inclusive production; planning and management of the territory, cities, natural resources and the environment.* | SP Outcome 3 - Build resilience to shocks and crises | Terminal Evaluation of GEF Address Urgent Coastal Adaption Needs & Capacity Gaps Angola Project | UNDP, MINAMB, UNEP, GEF | UNDP/GEF | Project  | February 2021 | $30,000 | GEF project funds |
| ***Outcome 2*** *By 2022, the vulnerable population is resilient to climate change and disaster risk with sustainable and inclusive production; planning and management of the territory, cities, natural resources and the environment.* | SP Outcome 3 - Build resilience to shocks and crises | Mid-term evaluation of GEF Marine Protected Areas Project | UNDP, MINAMB, MINPESMAR, GEF | UNDP/GEF | Project  | May 2021 | $30,000 | GEF project funds |
| ***Outcome 3:*** *By 2022, citizens participate & exercise governance oversight, people have access to justice and human rights are observed in a context of regional peace and stability.*  | SP Outcome 2 - Accelerate structural transformations for sustainable development | Final Evaluation Realization of a Justice and Inclusive Society Project | MASMAFU, MINJUDH, MININT, PGR, Ombudsman, CSOs |  | Project | July 2021 | $15,000 | M&E project Budget |
| ***Outcome 2*** *By 2022, the vulnerable population is resilient to climate change and disaster risk with sustainable and inclusive production; planning and management of the territory, cities, natural resources and the environment.* | SP Outcome 3 - Build resilience to shocks and crises | Terminal Evaluation of GEF LDCF/ climate-resilience Angola´s Cuvelai River Basin Project | UNDP, MINAMB, IDA, GABHIC, INRH, Civil Protection, GEF, ADPP, DW, local government Cunene | UNDP/GEF | Project  | February 2022 | $30,000 | GEF project funds |
| ***Outcome 3*** *By 2022, citizens participate & exercise governance oversight, people have access to justice and human rights are observed in a context of regional peace and stability.* | SP Outcome 2 - Accelerate structural transformations for sustainable development | Mid-term evaluation “Local Assistance for Local Government” Project | MAT, MASFAMU, Parliament, CSOs |  | Project | May 2022 | $15,000 | M&E project Budget |
| ***Outcome 2*** *By 2022, the vulnerable population is resilient to climate change and disaster risk with sustainable and inclusive production; planning and management of the territory, cities, natural resources and the environment.*  | SP Outcome 3 - Build resilience to shocks and crises | Terminal Evaluation of Expansion & Strengthening Angola Protect Areas System Project | UNDP, INBAC, GEF | UNDP/GEF | Project  | July 2022 | $30,000 | GEF project funds |
| ***Outcome 3****By 2022, citizens participate & exercise governance oversight, people have access to justice and human rights are observed in a context of regional peace and stability.* | SP Outcome 2 - Accelerate structural transformations for sustainable development | Portfolio evaluation: Strengthening Governance Institutions Portfolio  | MINJUDH, MININT, PGR, Ombudsman, CSOs |  | Portfolio | October 2022 | $35,000 | TRAC Funds |
|  | All Outcomes |  UNDAF Terminal Evaluation | MEP led-Line-Ministries-Implementing Partners-Development Partners-UN Cooperating Agencies | RCO | UNDAF Evaluation | September 2021 | $30,000 | UNCT |